Islamic Republic of Mauritania

Ministry of Economic Affairs and Development

Mauritania Resilience and Productive Safety Nets Program (P508831) (Part 2 – Investment Project Financing Component)

Negotiated

ENVIRONMENTAL and SOCIAL

COMMITMENT PLAN (ESCP)

April 29, 2026

ENVIRONMENTAL AND SOCIAL COMMITMENT PLAN

- The Islamic Republic of Mauritania, (the Recipient) will implement the Mauritania Resilience and Productive Safety Nets Program (Operation), with the involvement of the Ministry of Economic Affairs and Development as set out in the Financing Agreement and the Grant Agreement (the "Agreements").  The International Development Association (the "Association") has agreed to provide financing for the Program, as set out in the referred agreements. The operation includes a Program-for-Results (Program) component, as outlined in Part 1 of Schedule 1 of each Agreement, and an Investment Project Financing (Project) component, detailed in Part 2 of the same schedule.

- The Recipient shall ensure that the Project is carried out in accordance with the Environmental and Social Standards (ESSs) and this Environmental and Social Commitment Plan (ESCP), in a manner acceptable to the Association. The ESCP is a part of the Grant Agreement. Unless otherwise defined in this ESCP, capitalized terms used in this ESCP have the meanings ascribed to them in the Agreements.

- Without limitation to the foregoing, this ESCP sets out material measures and actions that the Recipient shall carry out or cause to be carried out, including, as applicable, the timeframes of the actions and measures, institutional, staffing, training, monitoring, and reporting arrangements and grievance management. The ESCP also sets out the environmental and social (E&S) instruments that shall be adopted and implemented under the Project, all of which shall be subject to prior consultation and disclosure, consistent with the ESS, and in form and substance, and in a manner acceptable to the Association. Once adopted, said E&S instruments may be revised from time to time with the prior written agreement by the Association. As provided for under the referred Agreement, the Recipient shall ensure that there are sufficient funds available to cover the costs of implementing the ESCP.

- As agreed by the Association and the Recipient, this ESCP will be revised from time to time, if necessary, during project implementation to reflect adaptative management of Project changes and unforeseen circumstances or in response to project performance. In such circumstances, the Recipient and the Association agree to revise the ESCP to reflect on these changes through an exchange of letters signed between the Association and the Recipient. The Recipient shall promptly disclose the updated ESCP.

- The subsection on “Indicators for Implementation Readiness” below identifies the actions and measures to be monitored to assess Project readiness to begin implementation in accordance with this ESCP. Nevertheless, all actions and measures in this ESCP shall be implemented as set out in the

“Timeframe” column below, irrespective of whether they are listed in the referred subsection.

| MATERIAL MEASURES AND ACTIONS |  | TIMEFRAME | RESPONSIBILE ENTITY |
| --- | --- | --- | --- |
| IMPLEMENTATION ARRANGEMENTS AND CAPACITY SUPPORT |  |  |  |  |
| A | ORGANIZATIONAL STRUCTURE Maintain PA’s existing project coordination unit (PCU), with qualified staff and sufficient resources to support management of ESHS risks and impacts of the Project, including (1) an environmental specialist and (2) a social development specialist. | Recruit the Environmental Specialist and Social Development Specialist no later than 3 months after the signing of the grant agreement, and then maintain these two (2) experts throughout the implementation of the project | PCU |
| B | CAPACITY BUILDING PLAN/MEASURES Organize a series of training sessions for Program stakeholders, including community members, project workers, and consultants, covering (but not limited to) the following topics: - World Bank Environmental and Social Framework (ESF): including the Environmental and Social Standards (ESS), key aspects of environmental and social assessments (particularly complex issues identified in ESIAs), workforce management, stakeholder mapping and engagement, emergency preparedness and response, occupational and community health and safety, as well as environmental and social monitoring and reporting. - Relevant Mauritanian legislation on environmental and social protection. - Grievance Redress Mechanism (GRM): procedures for registering and handling complaints, documentation and processing steps, and practical guidance on the use of the mechanism by different stakeholder groups. - Prevention and mitigation of Gender-Based Violence (GBV) and Exploitation, Abuse, and Sexual Harassment (EAS); child protection; gender equality; and inclusion of persons with disabilities. | From the first year of the Project's implementation, and throughout its implementation | PCU |
| MONITORING AND REPORTING |  |  |  |
| C | REGULAR REPORTING Prepare and submit to the Association regular monitoring reports on the environmental, social, health and safety (ESHS) performance of the Program, including but not limited to the implementation of the ESCP, status of preparation and implementation of the E&S instruments required under the ESCP, stakeholder engagement activities, functioning of the grievance mechanism(s), including grievances related to the resettlement and cases of sexual exploitation and abuse, sexual harassment (SEA/SH) and violence against children (VAC) | Submit semi-annual reports on Program activities to the Association, throughout Project implementation, starting after the Effective Date. Submit each report to the Association no later than 15 days after the end of each reporting period. | PCU |
| E | INCIDENTS AND ACCIDENTS Promptly notify the Association of any incident or accident related to the Program, which has or is likely to have a significant adverse effect on the environment, the affected communities, the public or workers, including, inter alia, cases of sexual exploitation and abuse (SEA), sexual harassment (SH) and accidents that result in death, serious or multiple injury. Provide sufficient details regarding the scope, severity and possible causes of the incident or accident, indicating immediate measures taken or that are planned to be taken to address it, and any information provided by any contractor and/or supervising firm, as appropriate. Subsequently, at the Association's request, prepare a report on the incident or accident and propose any measures to address it and prevent its recurrence. | Notify the Association no later than 48 hours after learning of the incident or accident Provide subsequent report to the Association within a timeframe acceptable to the Association. Provide review report and Corrective Action Plan to the Association no later than 10 days following the submission of the initial notice, unless there is a different timeframe is agreed to in writing by the Association. | PCU |
| ESS 1: ASSESSMENT AND MANAGEMENT OF ENVIRONMENTAL AND SOCIAL RISKS AND IMPACTS |  |  |  |
| 1.1 | ENVIRONMENTAL AND SOCIAL ASSESSMENTS Develop and implement environmental and social risk management measures, to be incorporated into the Project Operations Manual (POM), in alignment with the applicable Environmental and Social Standards (ESSs) and the Recipient’s environmental and social framework. | Integrate the environmental and social risk management measures during the preparation of the POM and ensure their implementation throughout the duration of the Project. | PCU |
| 1. 2 | BORROWER ENVIRONMENTAL AND SOCIAL (ES) FRAMEWORK - Ensure that the Program’s Environmental, Social, Health, and Safety (ESHS) risks and impacts including those related to labor and working conditions—are addressed in line with this ESCP and the Recipient’s Environmental and Social Framework. This includes, among other elements, the country’s relevant policies, laws, and institutional arrangements at national, departmental, and local levels, as well as applicable regulations, procedures, and implementation capacities. - Immediately inform the Association of any modifications to the Recipient’s Environmental and Social (ES) Framework that could significantly hinder the effective management of the Project’s ESHS risks and impacts in accordance with the ESSs. The notification should include details of any immediate or planned measures to address the changes and associated risks, in a manner acceptable to the Association. If the Association determines that the changes negatively impact on the Project’s ESHS risk management, the Recipient shall agree to implement corrective measures and update the ESCP accordingly to reflect the agreed actions. | - Throughout Project implementation. - Inform the Association without delay upon becoming aware of any changes to the Recipient’s ES Framework. If the Association requests further action, these measures shall be incorporated into a revised version of the ESCP, in accordance with paragraph 4 of the Initial Section of this ESCP. | PCU |
| 1.3 | TECHNICAL ASSISTANCE Ensure that all consultancies, studies, capacity-building efforts, training, and other technical assistance activities under the Project are conducted based on terms of reference approved by the Association and aligned with the Environmental and Social Standards (ESSs). Subsequently, ensure that the deliverables from these activities adhere to the approved terms of reference. | Throughout project implementation | PCU |
| ESS 2: WORK AND WORKING CONDITIONS |  |  |  |  |
| 2 | LABOR MANAGEMENT PROCEDURES Ensure that workers are engaged in the implementation of the Activities consistent with ESS2. To this end, ensure that the following measures are carried out: Provide workers with information and documentation that is clear and understandable regarding their terms and conditions of employment through written contracts setting out their rights, including, inter alia, rights related to hours of work, wages, overtime, compensation and benefits, as well as written notice of termination of employment, and details of severance payments, as applicable; Implement occupational health and safety (including, as applicable, personal protective equipment, and emergency preparedness and response) measures, taking into account the General Environmental, Health and Safety Guidelines (EHSGs), and other relevant Good International Industry Practice (GIIP) and, as appropriate, the industry specific EHSGs and other Good International Industry Practice (GIIP); Implement measures, as applicable, to, inter alia: (i) prevent the use of all forms of forced labor and child labor; (ii) enable workers to benefit from, inter alia, access to grievance and redress mechanisms without fear of retaliation; and effective freedom to form and join workers organizations or alternative mechanisms for expressing their concerns and protect their rights related to labor and working conditions; Develop a code of conduct for workers, which shall include measures to prevent and respond to SEA and SH cases; and Incorporate the relevant requirements above in the ESHS specifications of the procurement documents and contracts with third parties engaged for the implementation of the Activities. | Develop and integrate detailed labor management procedures during the preparation of the POM and subsequently carry out the measures throughout the implementation of the Activities | PCU |
| ESS 3: RATIONAL USE OF RESOURCES AND POLLUTION PREVENTION AND MANAGEMENT |  |  |  |  |
| 3.1 | WASTE MANAGEMENT PLAN Integrate and implement the e-Waste Management measures within the POM to address e-waste management, in alignment with ESS3 and the Recipient’s Environmental and Social Framework. | Finalize and adopt the electronic Waste Management measures in parallel with the adoption of the POM, and ensure its implementation is sustained throughout the Project’s execution period. | PCU |
| ESS 4: COMMUNITY HEALTH AND SAFETY |  |  |  |  |
|  | COMMUNITY HEALTH AND SAFETY Adopt and implement appropriate measures for the safe disposal of e-waste within the POM to prevent harm to community health and safety, in line with environmental and social standards. | Adopt the e-Waste Management measures within the same timeframe as the ESMP and POM and implement it throughout Project implementation to ensure safe e-waste disposal and safeguard community health and safety. | PCU |
| 4.2 | SEA AND SH RISKS Prepare, consult on, disclose, adopt, and implement a SEA/SH Action Plan, to assess and manage the risks of SEA and SH. | Prepare and adopt the SEA/SH Action Plan within the same timeframe as the POM and implement it throughout the Program implementation period to address risks related to sexual exploitation, abuse, and harassment. | PCU |
| ESS 5: LAND ACQUISITION, RESTRICTIONS ON LAND USE AND INVOLUNTARY RESETTLEMENT |  |  |  |  |
| Not relevant. |  |  |  |  |
| ESS 6: BIODIVERSITY CONSERVATION AND SUSTAINABLE MANAGEMENT OF LIVING NATURAL |  |  |  |  |
| Not relevant. |  |  |  |  |
| ESS 7: INDIGENOUS PEOPLES/SUB-SAHARAN AFRICAN HISTORICALLY UNDERSERVED TRADITIONAL LOCAL |  |  |  |  |
| Not relevant. |  |  |  |  |
| ESS 8: CULTURAL HERITAGE |  |  |  |  |
| Not relevant. |  |  |  |  |
| ESS 9: FINANCIAL INTERMEDIARIES |  |  |  |  |
| Not relevant. |  |  |  |  |
| ESS 10: STAKEHOLDER ENGAGEMENT AND INFORMATION DISCLOSURE |  |  |  |  |
| 10.1 | STAKEHOLDER ENGAGEMENT PLAN PREPARATION AND IMPLEMENTATION Prepare, consult on, disclose, adopt and implement a Stakeholder Engagement Plan (SEP) for the Project, consistent with ESS10, which shall include measures to, among others, provide stakeholders with timely, relevant, understandable, and accessible information, and consult with them in a culturally appropriate manner, which is free of manipulation, interference, coercion, discrimination, and intimidation. | The SEP, which has been prepared and disclosed before appraisal, will be implemented throughout Project implementation. | PCU |
| 10.2 | PROJECT GRIEVANCE MECHANISM Establish, publicize, maintain, and operate an accessible grievance mechanism to receive and facilitate resolution of concerns and grievances in relation to the Project, promptly and effectively, in a transparent manner that is culturally appropriate and readily accessible to all Project-affected parties, at no cost and without retribution, including concerns and grievances filed anonymously, in a manner consistent with ESS10. The grievance mechanism shall be equipped to receive, register, and facilitate the resolution of GBV, SEA/SH complaints, including through the referral of survivors to relevant gender-based violence service providers, all in a safe, confidential, and survivor-centered manner. | Establish the GM no later than three months after the Effective Date and maintain and operate it throughout the implementation of the Project | PCU |
| INDICATORS FOR IMPLEMENTATION READINESS |  |  |  |  |
| The following actions demonstrate readiness for implementation: i) Retaining environmental and social specialists within the project implementation unit; ii) Strengthening the capacity of E&S personnel in the implementing entities on the Environmental and Social Framework (ESF); iii) Meeting any required environmental and social effectiveness or disbursement conditions, if applicable. iv) Integrating environmental and social considerations into the Program Operations Manual (POM); v) Fulfilling any other project-specific environmental and social requirements necessary for implementation readiness. |  |  |  |